## Sheet1
Risk ID | Risk Author | Registered Date | Category |  | Risk Description | T/O | Assessment |  |  | Expected Value (Prob*Impact) | Risk Response Category | Risk Owner | Risk Actionee | Risk Status
|  |  | Internal | External |  |  | Probability % | Proximity (Days) | Impact (£)
C1 | Anusha | 2025-02-01 | Financial |  | Cause: Unforeseen expenses in software customization | Threat | 70 | 90 | 30000, High | 21000 | Reduce Investment | Mudasir | Anusha | Active
Event:Project exceeds £75,000 budget
Effect:Increased costs and potential funding issues
C2 | Anusha | 2025-02-01 |  | Compliance&Legal | Cause:Inadequate cybersecurity measures | Threat | 30 | 120 | 50000, High | 15000 | Avoid the Project | Mudasir | Anusha | Active
Event: Data privacy breach occurs
Effect:Regulatory fines, reputational damage, and customer loss
C3 | Anusha | 2025-02-01 | Operational |  | Cause: Vendor delays and internal resource constraints | Threat | 50 | 60 | 25000, High | 12500 | Reduce Investment | Mudasir | Anusha | Active
Event:System implementation is delayed
Effect: Disruptions to daily operations and loss of productivity
C4 | Anusha | 2025-02-01 |  | Customer Satisfaction | Cause: Insufficient testing before launch | Opportunity | 60 | 30 | 12000, medium | 7200 | Accept the Project | Mudasir | Anusha | Active
Event:System bugs and usability issues
Effect: Poor user experience and customer dissatisfaction
C5 | Anusha | 2025-02-01 | Technical |  | Cause: Incompatibility between new and existing systems | Opportunity | 40 | 45 | 15000, medium | 6000 | Reduce Investment | Mudasir | Anusha | Active
Event: System integration fails
Effect: Increased downtime and additional development costs
C6 | Anusha | 2025-02-05 |  | Regulatory & Compliance | Cause: Changes in data protection laws | Threat | 50% | 60 | 20,000 High | 10000 | Avoid the Project | Mudasir | Anusha | Active
Event: System fails to comply with new legal requirements.
Effect: Legal penalties and reputational damage.
C7 | Anusha | 2025-02-05 |  | Cybersecurity | Cause: Increased cyber threats to IoT devices. | Threat | 80% | 30 | 60000 High | 48000 | Avoid the Project | Mudasir | Anusha | Active
Event: Data breach occurs.
Effect: Customer data compromised, legal & financial consequences.
C8 | Anusha | 2025-02-05 |  | Vendor Reliability | Cause: Key third-party vendor fails to deliver on time. | Threat | 65% | 90 | 40000 High | 26000 | Reduce Investment | Mudasir | Anusha | Active
Event: Delayed ERP implementation
Effect: Project timeline is extended, affecting other milestones.